## MasteringMFAcquisitions
Initial Tasks
Task ID | Task Description |  |  |  |  | Complete? |  |  |  |  | Notes
1 | Syndication Tasks
1.1 | File Form D
1.2 | Create PPM
1.3 | Create Docusign version for investors
1.4 | Get EIN for property entity
1.5 | Get EIN for investor entity
1.6 | Get EIN for GP entity
1.7 | Create property entity
1.8 | Create investor entity
1.9 | Create GP entity
1.1 | Create wire instructions
2 | Investor Relations / Marketing Tasks
2.1 | Create OM
2.2 | Obtain onsite drone footage
2.3 | Create video for unit walkthroughs
2.4 | Obtain property pictures (interior & exterior)
2.5 | Add offering to portal
2.6 | Create promotional video
2.7 | Schedule live webinar
2.8 | Rod to mention on podcast intro
2.9 | Email blast to potential investors
3 | After PSA Executed
3.1 | Create entity and receive formation docs
3.2 | Certificate of existence - S.O.S.
3.3 | Certificate of formation
3.4 | Certificates of Account Status/Tax Franchise Status - Comptroller
3.5 | Articles of Organization (Form SS-4)
3.6 | Set up On-Site Due Diligence
3.7 | Order Third Party Reports
3.8 | All environmental assessments
3.9 | Ordered
3.1 | Read
3.11 | Recommendation
3.12 | Zoning compliance report
Initial Tasks Continued
Task ID | Task Description |  |  |  |  | Complete? |  |  |  |  | Notes
3.13 | Ordered
3.14 | Read
3.15 | Recommendation
3.16 | Asbestos survey
3.17 | ACM O&M Plan (If Needed)
3.18 | Property condition assessments:
3.19 | Ordered
3.2 | Read
3.21 | Recommendation
3.22 | PSA Timeline
3.23 | Initial Deposit
3.24 | Due Diligence Period
3.25 | Second Deposit
3.26 | Title Review
3.27 | Inspection Period Complete
3.28 | Assumption Approval
4 | KPI Tasks
4.1 | Assignment of contract
4.2 | UCC searches
4.3 | Form 6460
4.4 | Credit authorization form
4.5 | KPI financials
4.6 | KPI REOs
4.7 | Full bank statements
Due Diligence Tasks
Task ID |  | Task Description |  | Complete? |  |  |  |  | Notes
4 |  | Due Diligence Tasks
4.1 |  | Financial Due Diligence
4.1.1 |  | Real property tax bills - 2 years
4.1.2 |  | Real property tax appeals - 3 years
4.1.3 |  | Tenant ledger
4.1.4 |  | Rent roll (current)
4.1.5 |  | Tenant payment history - 24 months
4.1.6 |  | Tenant security deposits (including letters of credit)
4.1.7 |  | Operating budget - current
4.1.8 |  | Delinquency/Aging report - current
4.1.9 |  | YE Financials: Income, P&L, CF Statements - 3 years
2010-04-01 |  | Trailing 12 months operating statement to current
2011-04-01 |  | On-site staff & payroll
2012-04-01 |  | Tenant financial information (majors)
4.2 |  | Leases and Contracts
4.2.1 |  | Utility leases (water, electric, gas)
4.2.2 |  | Franchise agreements (If applicable)
4.2.3 |  | Contracts (compare to TC Schedule B)
4.2.4 |  | HAP contracts
4.2.5 |  | Commercial leases
4.2.6 |  | Oil & Gas leases
4.2.7 |  | Ground leases
4.2.8 |  | Cable contracts
4.2.9 |  | Vendor contracts
2010-04-02 |  | Billboard contracts
2011-04-02 |  | Laundry lease (check with title) - most critical
2012-04-02 |  | Landscape/lawn contracts
2013-04-02 |  | All warranties (i.e. roof)
4.3 |  | Third Party Reports/Inspections
4.3.1 |  | All documents for construction and engineering of the improvements
4.3.2 |  | ALTA survey (most up-to-date)
4.3.3 |  | Updated survey (if needed)
4.3.4 |  | Parcel map (most-up-to-date)
4.3.5 |  | Appraisal (most recent)
Due Diligence Tasks Continued
Task ID |  | Task Description |  | Complete? |  |  |  |  | Notes
4.3.6 |  | Building Inspection Reports (roof, HVAC, plumbing)
4.3.7 |  | Structural evaluation reports (if needed)
4.3.8 |  | Geotechnical/soil reports (if needed)
4.3.9 |  | ADA compliance survey/issues
2010-04-03 |  | Fire sprinkler rating/alarm-inspections
2011-04-03 |  | Elevator permits/inspections
2012-04-03 |  | Natural hazards disclosure report
2013-04-03 |  | Any forensic studies prepared
2014-04-03 |  | Fire & life safety
2015-04-03 |  | Termite report
4.4 |  | Misc. Documents
4.13 |  | Tenant correspondence/complaints
4.31 |  | Property
4.32 |  | Blank lease
4.34 |  | Property manager resume
4.35 |  | Pictures
4.36 |  | Brochure
4.37 |  | Inventory
4.43 |  | Any licenses/permits
4.47 |  | Asphalt (parking lot)
4.49 |  | Proposals to remedy any significant physical deficiency
4.5 |  | Certificate of occupancy
Title & Insurance Tasks
Task ID |  | Task Description |  |  | Complete? |  |  |  |  | Notes
8 |  | Insurance Tasks
8.1 |  | Seller's insurance
8.2 |  | Insurance claims/Loss-run histories - 5 years
8.3 |  | Insurance quotes
8.4 |  | Certificate of liability insurance (Accord 25)
8.5 |  | With lender
8.6 |  | With management company
8.7 |  | Evidence of commercial property insurance (Accord 28)
8.8 |  | With lender
8.9 |  | With management company
8.1 |  | Evidence of property insurance (Accord 27)
8.11 |  | With lender
8.12 |  | With management company
9 |  | Title Tasks
9.1 |  | Seller's title commitment
9.2 |  | Title commitment/title report
9.3 |  | Easements, access rights, option agreements, licenses
9.4 |  | Title pro forma "marked up title commitment"
9.5 |  | Survey Affidavit
9.6 |  | Most recent title insurance policies and/or survey
9.7 |  | Other instruments that create liens, encumbrances, or other charges
9.8 |  | Final OTP
9.9 |  | Recorded Documents - Warranty deeds / DOT / Assignments
Acquisition Checklist
Property Management Tasks
Task ID |  | Task Description | Complete? |  |  |  | Notes
5 |  | Acquisitions Tasks
5.1 |  | Capital improvement budget
5.2 |  | Contract vendors for budget for lender approval
5.3 |  | CapEx Schedule and Tis - 12 months
5.4 |  | Deferred property maintenance list
5.5 |  | Org Chart Draft - structure (add lender version)
5.6 |  | Sources & uses form
5.7 |  | Replacement and improvement form
5.8 |  | Provide investor on deal with wire amounts and addresses
5.9 |  | Operating agreement
6 |  | Asset Manager Tasks
6.1 |  | Open saving account
6.2 |  | Wiring instructions - sent to title company
6.3 |  | Create W9
6.4 |  | Funds transfer agreement
7 |  | Property Management Tasks
7.1 |  | Budget
7.2 |  | Send POC for takeover
7.3 |  | Ask if inventory will stay or leave
7.4 |  | Ask if staff will stay or leave
7.5 |  | Send info regarding property: see attached
7.6 |  | Open entity bank account
7.7 |  | ACH Form
7.8 |  | Voided check - operating account
7.9 |  | Wiring instruction
7.1 |  | Executed management agreement
Acquisition Checklist
Pre-Closing Tasks
Task ID |  | Task Description |  |  |  |  | Complete? |  |  |  |  | Notes
10 |  | Prior to closing tasks
10.1 |  | Final Rehab budget
10.2 |  | Rate lock
10.3 |  | Good faith deposit
10.4 |  | Commitment letter
10.5 |  | Reimbursement (legal, appraisal, DD, WBCC, rate lock, EDM, background check)
10.6 |  | Asset manegement fee
10.7 |  | Settlement statement
Post-Closing Tasks
Task ID |  | Task Description | Complete? |  |  |  |  | Notes
11 |  | Post Closing Tasks
11.1 |  | CPA memo, closing statement, org. chart
11.2 |  | Website update
11.3 |  | Pay intermediaries
11.4 |  | Pay legal
11.5 |  | Lender's appraisal
11.6 |  | Bind insurance coverage
11.7 |  | Collect LLC formation docs from all equity partners
11.8 |  | Send management company:
2011-08-01 |  | Settlement statement
2011-08-02 |  | Executed loan docs
2011-08-03 |  | Property tax
2011-08-04 |  | Insurance
2011-08-05 |  | Operating agreement
2011-08-06 |  | Org chart after the split, if any
2011-08-07 |  | Paid out of closing with copies of invoices, if any
2011-08-08 |  | Executed management agreement
2011-08-09 |  | Reimbursements allocation
11.9 |  | Asset manager's to-do list
2011-09-01 |  | Lender POC
2011-09-02 |  | Bid/contracts for property work
2011-09-03 |  | Executed AMP
2011-09-04 |  | Welcome meeting - onsite visit (within 1 week)
2011-09-05 |  | Set up reno calls with regional, contractor (weekly calls)
2011-09-06 |  | Migrate files (Groom to asset management standards)
2011-09-07 |  | Update to REO (KPs)
11.1 |  | To investors/captive insurance (a week after):
2011-10-01 |  | Closing binder w/introduction packet
2011-10-02 |  | Settlement statement
2011-10-03 |  | Survey
2011-10-04 |  | Operating agreement
2011-10-05 |  | Recorded documents - Warranty deeds/DOT/Assignment
2011-10-06 |  | Loan documents
Post-Closing Tasks Continued
Task ID |  | Task Description | Complete? |  |  |  |  | Notes
2011-10-07 |  | Loan policy
2011-10-08 |  | Owner's policy of title insurance
2011-10-09 |  | Third party reports
2010-11-10 |  | Appraisal
2011-11-10 |  | Reno budget

## Questions To Ask A Prospective
Name
Email
Mailing Address
Date of Call
How did you hear about us?
What is your occupation?
Are you an accredited investor?
What kind of investing experience do you have?
What are your goals by potentially investing in real estate syndications?
We invest in B and C value-add properties with an average Cash on Cash of 7-10% per year and projected AAR of 13-15%, with a holding period of 5-7 years -- how does that fit with your investment criteria?
If we brought you an opportunity that fits your criteria, how much would you feel that you would be comfortable investing?
What’s the biggest challenge right now as you evaluate investment options?
What could we do to help you make better investment decisions?
i.e. content, videos, webinars, events, property tours, etc?
If so, what medium (email, video, webinar), frequency, and duration?
What questions do you have for me?
Have you ever invested passively?
Do you own any real estate?
What are your investment goals?
Cash flow or quick hit?
Do you understand how being an LP in a syndication works?
Do you know if you're accredited?
How quickly do you need your capital back?
What do you know about multifamily?